Monthly Project Report

Northstar Customer Platform

Document role: Current monthly performance evidence

Reporting period: April 2026

Reporting period key: 2026-04-01

Report date: 2026-04-30

Management status: Needs attention. Forecast cost is 2% above the approved budget, Go-Live is forecast 7 days late, and one new controlled high risk is open.

# Current control snapshot

| Measure | Plan / baseline | April current value |
| --- | --- | --- |
| Budget | USD 1,200,000 | Forecast at completion: USD 1,224,000 |
| Cost to date | - | Actual cost: USD 455,000 |
| Overall progress | 40% planned | 34% actual |
| Production Go-Live | 2026-09-30 | Forecast: 2026-10-07 |
| Schedule movement | 0 days | 7 calendar days late |

# Current risk evidence

| Risk ID | Severity | Status and control |
| --- | --- | --- |
| R-014 | High | Open; owner: Integration Lead; mitigation: add capacity test; due 2026-05-15. |

Explicit April risk counts: 0 open critical risks; 1 open high risk; 0 high risks missing an owner or mitigation; 0 increased risks; 1 new high risk; maximum mitigation overdue is 0 days.

# PMO decision

Keep the approved baseline unchanged. The Integration Lead will run the capacity test before the May steering committee and report whether the 7-day forecast delay can be recovered.