Monthly Progress Report

Alpha Infrastructure Program

Reporting period: May 2026 | Prepared for: Capital Delivery Board

# Executive narrative

The program needs management attention. Forecast cost is 4.0 percent above baseline, Building A completion is fourteen days late, and a high-risk mitigation is seven days overdue.

# Current control position

| Field | Current evidence |
| --- | --- |
| Reporting period | May 2026 |
| Approved budget | USD 4,300,000 |
| Current forecast at completion | USD 4,472,000 |
| Current actual cost | USD 2,530,000 |
| Approved milestone | Building A installation complete on 2026-05-25 |
| Current forecast milestone | Building A installation complete on 2026-06-08 |
| Open critical risks | 0 |
| Open high risks | 1 |
| High risks missing owner or mitigation | 0 |
| Increased high risks | 0 |
| New high risks | 0 |
| Maximum mitigation overdue days | 7 |

# Delivery progress

| Measure | Planned | Actual |
| --- | --- | --- |
| Overall progress | 54% | 43% |

# Management decision

Approve the recovery shift and assign a due date for the overdue mitigation.

# Evidence note

Read this report with the cost report, risk register, and issue log for the same reporting period. Where documents disagree, the PMO must verify the source before approving a report.