Monthly Project Report

Northstar Customer Platform

Document role: Current monthly performance evidence

Reporting period: May 2026

Reporting period key: 2026-05-01

Report date: 2026-05-31

Management status: Critical. Forecast cost is 8% above the approved budget, Go-Live is forecast 21 days late, and critical or uncontrolled risk requires escalation.

# Current control snapshot

| Measure | Plan / baseline | May current value |
| --- | --- | --- |
| Budget | USD 1,200,000 | Forecast at completion: USD 1,296,000 |
| Cost to date | - | Actual cost: USD 690,000 |
| Overall progress | 60% planned | 46% actual |
| Production Go-Live | 2026-09-30 | Forecast: 2026-10-21 |
| Schedule movement | 0 days | 21 calendar days late |

# Current risk evidence

| Risk ID | Severity | Status and control |
| --- | --- | --- |
| R-014 | High | Open and increased; owner: Integration Lead; capacity mitigation overdue by 21 days. |
| R-021 | Critical | Open; data migration rehearsal failed; owner: Recovery Manager; mitigation in progress. |
| R-022 | High | Open and new; no owner and no mitigation has been assigned. |

Explicit May risk counts: 1 open critical risk; 2 open high risks; 1 high risk missing an owner or mitigation; 2 increased risks; 1 new high risk; maximum mitigation overdue is 21 days.

# Required management decision

Escalate the recovery plan to the steering committee. Assign an owner and mitigation to R-022, approve the data migration recovery resources, and decide whether to rebaseline only after the impact is independently verified.