Monthly Project Report

Harbor City Service Portal

Document role: Current monthly performance evidence

Reporting period: April 2026

Reporting period key: 2026-04-01

Report date: 2026-04-30

Management status: On track. Forecast cost remains below the approved budget, Go-Live is forecast 5 days early, and the known high risk is controlled.

# Current control snapshot

| Measure | Plan / baseline | April current value |
| --- | --- | --- |
| Budget | USD 1,000,000 | Forecast at completion: USD 980,000 |
| Cost to date | - | Actual cost: USD 372,000 |
| Overall progress | 40% planned | 42% actual |
| Production Go-Live | 2026-09-30 | Forecast: 2026-09-25 |
| Schedule movement | 0 days | 5 calendar days early |

# Current risk evidence

| Risk ID | Severity | Status and control |
| --- | --- | --- |
| R-006 | High | Open and stable; owner: Service Lead; mitigation: weekly adoption review; due 2026-06-15. |

Explicit April risk counts: 0 open critical risks; 1 open high risk; 0 high risks missing an owner or mitigation; 0 increased risks; 0 new high risks; maximum mitigation overdue is 0 days.

# PMO decision

Maintain the approved baseline. Continue the weekly adoption review and preserve the current delivery sequence because cost, schedule, and risk controls remain within the approved plan.