Monthly Project Report

Harbor City Service Portal

Document role: Current monthly performance evidence

Reporting period: May 2026

Reporting period key: 2026-05-01

Report date: 2026-05-31

Management status: On track. Forecast cost improved to 4% below budget, delivery is forecast 10 days early, and no critical or uncontrolled risk is open.

# Current control snapshot

| Measure | Plan / baseline | May current value |
| --- | --- | --- |
| Budget | USD 1,000,000 | Forecast at completion: USD 960,000 |
| Cost to date | - | Actual cost: USD 558,000 |
| Overall progress | 60% planned | 64% actual |
| Production Go-Live | 2026-09-30 | Forecast: 2026-09-20 |
| Schedule movement | 0 days | 10 calendar days early |

# Current risk evidence

| Risk ID | Severity | Status and control |
| --- | --- | --- |
| R-006 | High | Open and stable; owner: Service Lead; mitigation: weekly adoption review; due 2026-06-15. |

Explicit May risk counts: 0 open critical risks; 1 open high risk; 0 high risks missing an owner or mitigation; 0 increased risks; 0 new high risks; maximum mitigation overdue is 0 days.

# PMO decision

Maintain the approved baseline and current delivery approach. Keep R-006 under weekly review while protecting the cost saving and the 10-day schedule buffer through final readiness testing.