Project Baseline

Riverside Data Hub

This baseline defines the approved delivery reference used by the PMO to compare current performance against expected schedule, cost, governance, and assurance evidence.

# Project Control Profile

| Field | Value |
| --- | --- |
| Project Name | Riverside Data Hub |
| Sector | Digital services and data platform |
| Sponsor | Customer Operations Directorate |
| Project Manager | Maya Prasetyo |
| Baseline Budget USD | 500,000 |
| Assurance Cadence | Monthly PMO checkpoint with evidence-backed executive summary |

# Baseline Milestones

| Milestone | Baseline Date | Status | Planning Note |
| --- | --- | --- | --- |
| Requirements baseline approved | 2026-01-20 | Baseline | Scope signed off by product and operations |
| Data ingestion foundation complete | 2026-02-28 | Baseline | Core ingestion service and schema controls |
| API integration checkpoint | 2026-03-15 | Baseline | External service integration and load test |
| Operational readiness review | 2026-04-18 | Baseline | Runbook and support readiness approval |

# Governance and Assurance Requirements

Monthly executive summary must compare planned progress, actual progress, cost forecast, active risk exposure, and evidence readiness.

Schedule variance above 10 days or a missed dependency milestone requires a named recovery owner.

Forecast cost above approved baseline requires finance review and mitigation options.

High risks, overdue high-severity issues, and missing decision evidence must be escalated to the sponsor or steering committee.

Every management finding should be traceable to a source document, register, or approved record.