## Cost Report
Cost Item | Planned Cost USD | Actual Cost USD | Forecast Cost USD | Forecast Variance USD | Variance % | Status | Evidence Note
Energy audit and design | 520000 | 510000 | 540000 |  |  | Monitor | Minor consulting extension
Smart meter procurement | 1850000 | 1320000 | 1910000 |  |  | At Risk | Supplier price adjustment
Installation works | 1400000 | 610000 | 1540000 |  |  | At Risk | Night shift work may increase labor cost
Dashboard integration | 380000 | 90000 | 390000 |  |  | Normal | No major variance
Contingency | 150000 | 0 | 170000 |  |  | At Risk | Contingency may be exceeded
Total

## Project Metadata
Field | Value
Project Name | Alpha Infrastructure Program
Reporting Period | May 2026
Approved Baseline Budget USD | 4300000
Total Forecast Budget USD | 4550000