## Risk Register
Risk ID | Risk Description | Probability | Impact | Severity | Mitigation Plan | Owner | Status
R-201 | Building A installation delay affects dashboard pilot | High | Medium | High | Add weekend installation shift and daily constraint review | Installation Lead | Open
R-202 | Metering approval evidence incomplete | Medium | High | High | Collect approval records and update evidence register | Document Control | Open
R-203 | Supplier price adjustment increases forecast cost | Medium | Medium | Medium | Validate quotation and negotiate fixed price addendum | Procurement Lead | Open

## Project Metadata
Field | Value
Project Name | Alpha Infrastructure Program
Reporting Period | May 2026
Purpose | Active project risks for executive summary generation