## Issue Log
Issue ID | Issue Description | Owner | Due Date | Status | Severity | Current Note
I-301 | Customer master reconciliation fails tolerance threshold |  | 2026-06-05 | Overdue | Critical | No accepted workaround
I-302 | Cutover readiness evidence unavailable | PMO Controls | 2026-06-10 | Overdue | High | Go/no-go pack incomplete
I-303 | Recovery owner not confirmed in decision record |  | 2026-06-12 | Open | High | Accountability gap remains

## Project Metadata
Field | Value
Project Name | Orion ERP Recovery
Reporting Period | June 2026
Purpose | Open project issues and overdue actions for executive summary generation